## Sheet1
June	End of / June Goal	July	End of / July Goal	August	DEADLINE / AUGUST 31	September - November	FINAL DEADLINE / NOV 31 / (Official date TBD)
Analog / Scrap 555 Timer, introduce unwanted frequencies / Make signal generator with Arduino / Resistor net with variable resistor to control signal amplitude (voltage) to provide signal to ADS (Mid-June) / Try passive, active electrodes (aim for active filtering)	Signal generator -> / ADS -> Arduino -> RPI (single channel) / Showcase videos at June 30 event	Achieve 8-channel signal acquisition through electrodes	8-channel ADS -> / RPI -> Single channel graphing (Met competition requirements at this point)		Final 8-channel GUI / + Mobile App + / MindType Integration	Layout PCB, fabrication, form factor
Digital / Chip power up / Single channel communication with Arduino / Use Arduino as stepping stone to test the chip to make sure it is working (test noise, convert test signals)		Remove arduino, connect ADS directly to RPI		Digital and software merge
Software / Determine ADS data packet format / Queue data / Data transmission, deal with packet loss / Read data from a socket / Reformat data for later use / *Must first ensure that we can get data from ADS at 200Hz / Practice and things to learn / End Goal: / Get any data from the chip		Get ADS Data and plot graph of single channel / Store data in data format		Finalize GUI / Develop mobile app / Connect MindType to board